## To-do list
Order | Done?2 | Project 3 | Due By | Notes | Column1
0 | Yes | stocrates UID needs password reset | 2010-09-05 | OA
1 | Yes | mysql user access research. Sudo access for Dan, and admin access to mysql | 2010-09-05 | OA
2 | Yes | mysql server setup, insert tables | 2010-09-05 | DB
3 |  | push dummy data through phpMyAdmin |  | DB
3.1 | Yes | python email extraction prototype | 2011-04-18 | DB - Done
3.1 |  | python data insertion into DB via script
3.2 | Yes | update git and clone repository on server |  | OA
3.3 | Yes | install latest version of python (activestate python) |  | OA
4 | Yes | python email prototype, password entry through a config file. .stocrates |  | DB
4.1 |  | make python email prototype work on imac |  | OA/DB | In progress
4.2 | Yes | mysql db library |  | DB
4.3 | Yes | install mysqlDB extension (provided by daniel) |  | OA | http://sourceforge.net/projects/mysql-python/?source=dlp
5 | Yes | php myadmin explore (db admin for mysql) |  | OA
5.5 |  | update schema to link to image within email |  | DB
6 |  | figure out stock KPIs |  | OA
7 |  | upload latest stock predictions |  | OA
8 |  | fix imaplib |  | OA | In progress
9 |  | finance.yahoo API (simple csv method not using YahooQL) |  | DB | In progress
10 |  | python needs to extract stock's KPIs (market cap, current price etc)
10.1 |  | modifying the schema to add industry per stock |  | DB
11 |  | create stAR (stocrates Analyst Ranker) algorithm |  |  | In progress
11.1 |  | investigate open source license |  | OA
11.2 |  | research how eclipse can edit the file on a server (imac) |  | OA/DB
11.3 |  | Omer : set up eclipse to write code
12 |  | document stAR algorithm thus far |  | OA
13 |  | document HLA thus far |  | OA
14 |  | python2 (separate script) every night run to check against prediction
15 |  | python2 run algorithm to gauge analyst accuracy index. (0-100)
16 |  | python2 also needs to alert mailing list with report on prediction success
90 |  | see how cloud foundry can be used for stocrates (http://blog.cloudfoundry.com/) |  | OA
99 |  | php front-end data entry |  | delayed
99.1 |  | work on front-end which lets you query a Stock and provide recommendations based on analyst feedback with respective confidence rating |  | delayed
|  | php basic reporting (dump table) |  | OA
linuxVM: set up mongoDB
linuxVM: set up python
linuxVM: set up pymongo
linuxVM: set up pycharm
linuxVM: set up flask - basic
linuxVM: set up flask for search engine
linuxVM: set up drop box share where we will keep mongoDB database
linuxVM: set up mongo on the drop box
linuxVM: set up a local DB as well for testing.
mongoDB: input dummy DB based on schema
mongoDB: input dummy DB based on schema
mongoDB: figure out gridFS to handle BSON image insertion
AWS: set up python
AWS: set up pycharm
AWS: set up share with mongoDB
AWS: git import stocrates code
data: barrons old recommendations, create emails and send to gmail
data: barrons new newspapers, scour for recommendations, and annotate them
data: barrons new newspapers, take pictures, write rec text and send to gmail
R&D: scour IBD paper in allen library to see if it has recommendations
coding: