## To-do list
Order | Done?2 | Project 3 | Due By | Notes
0 | Yes | stocrates UID needs password reset | 2010-09-05 | OA
1 | Yes | mysql user access research. Sudo access for Dan, and admin access to mysql | 2010-09-05 | OA
2 | Yes | mysql server setup, insert tables | 2010-09-05 | DB
3 |  | python prototype to add random data to a table you plumb'd |  | DB
3.1 | Yes | python email extraction prototype | 2011-04-18 | DB - Done
3.2 | Yes | update git and clone repository on server |  | OA
3.3 | Yes | install latest version of python (activestate python) |  | OA
4 |  | python email prototype, password entry through a config file. .stocrates |  | OA
5 |  | php myadmin explore (db admin for mysql) |  | OA
6 |  | figure out stock KPIs |  | OA
7 |  | upload latest stock predictions |  | OA
|  | python backend | 2010-04-18
python data insertion into DB
python needs to extract stock's KPIs (market cap, current price etc)
|  | python need to do some extrapolation calculations as well |  | OA
python2 (separate script) every night run to check against prediction
python2 run algorithm to gauge analyst accuracy index. (0-100)
python2 also needs to alert mailing list with report on prediction success
|  | create accuracy index algorithim (ACCIA) |  | OA/DB whiteboard this
|  | php basic reporting (dump table) |  | OA
|  | php front-end data entry |  | delayed